## update the above sheet by addin
CI-ID | CI Name | Category | Version | Status | Description
DOC-01 | SCM Plan (SCMP) | Documentation | v1.0 | Draft | The rules for versioning and branching.
DOC-02 | CI Register | Documentation | v1.0 | Draft | This document itself.
DOC-03 | Software Requirements Spec | Documentation | v1.0 | Baselined | Project objectives and user stories .
DOC-04 | API Design (OpenAPI/Swagger) | Documentation | v1.0 | Baselined | The openapi.yaml file defining endpoints .
DOC-05 | System Architecture Diagram | Documentation | v1.0 | Baselined | High-level decoupled microservices overview .
SRC-01 | API Gateway Service | Source Code | v1.0 | Baselined | Go code for entry point routing .
SRC-02 | Auth Service | Source Code | v1.0 | Baselined | Go code for JWT and identity management .
SRC-03 | Inventory Service | Source Code | v1.0 | Baselined | Go code for item CRUD and search .
SRC-04 | Booking Service | Source Code | v1.0 | Baselined | Go code for rental lifecycles .
SRC-05 | Payment Service | Source Code | v1.0 | Baselined | Go code for Chapa Gateway integration .
SRC-06 | Notification Service | Source Code | v1.0 | Baselined | Go code for RabbitMQ consumers .
SRC-07 | React Frontend | Source Code | v1.0 | Baselined | React 18 / TypeScript source code .
INF-01 | Docker Compose File | Infrastructure | v1.0 | Baselined | docker-compose.yml orchestration .
INF-02 | RabbitMQ Event Schemas | Infrastructure | v1.0 | Baselined | JSON payload definitions for events .
INF-03 | MongoDB Schemas | Infrastructure | v1.0 | Baselined | Database collections for each service .
INF-04 | Environment Config (.env) | Infrastructure | v1.0 | Draft | The .env.example template .
VAL-01 | API Test Script (test_api.sh) | Validation | v1.0 | Baselined | test_api.sh integration script .
VAL-02 | Postman Collections | Validation | v1.0 | Baselined | E2E testing flows for Newman .
VAL-03 | Test Plan | Validation | v1.0 | Draft